Implementation Plan

AI Hair & Beauty Intelligence Platform

| Field | Value |
| --- | --- |
| Product | AI Hair & Beauty Intelligence Platform |
| Document | Implementation Plan (build runbook for Claude Code) |
| Version | 1.0 |
| Date | 23 June 2026 |
| Governs build of | PRD v1.0 · App Flow v1.0 · Tech Stack v1.0 · Design System v1.0 · Backend Schema v1.0 |
| Target launch | 01/08/2026 |
| Status | For build |

# 0. How to use this plan (rules for Claude Code)

1. Execute phases in order. Each phase has numbered steps and a Definition of Done (DoD). Do not start a phase until the previous phase's DoD passes.

2. Every step cites its governing document. When a step says "per Schema §4.4", that section is authoritative; this plan never overrides the five source documents — it sequences them.

3. Verification gates are mandatory. A gate (⛔) blocks progress until its automated checks pass. The RLS isolation gate and the migration-order gate are non-negotiable.

4. Commit discipline. One focused PR per step or tight group of steps; conventional commits (feat:, fix:, chore:, test:); every PR green on CI before merge. Never commit secrets; .env stays out of git.

5. Build vertically inside each module: migration → model → policy → RLS check → service/controller → API route → tests → frontend feature → tests. A module is "done" only when its backend tests, RLS gate, and frontend feature all pass.

6. If a step is ambiguous or a document is silent, stop and ask — do not improvise schema, auth, or design decisions.

# 1. Conventions & build approach

- Repository: single mono-repo. /backend (Laravel 12), /frontend (React 19 + Vite 7), /docs (the five source documents), /ops (deploy scripts, cron, env templates).

- Branching: main (always deployable), short-lived feature branches → PR → squash-merge.

- Definition of Done (global): code matches the governing doc; unit + feature tests written and passing; RLS respected; a11y (WCAG 2.1 AA) checks pass on touched UI; no linter/formatter errors (Pint, ESLint, Prettier); PR reviewed.

- Testing posture: backend Pest (feature + unit), frontend Vitest + Testing Library; a thin end-to-end happy-path suite for the critical flows (login, sale, distribution-confirm, reconciliation). Coverage target: every service method and every RLS policy class has a test.

- Three-layer authorization is always present (Schema §2.2): permission middleware → Laravel Policy → PostgreSQL RLS. No endpoint ships without all three.

- Environments: local (developer), ci (GitHub Actions or equivalent), production (DirectAdmin VPS). Parity via .nvmrc (Node 24) and the DirectAdmin PHP selector (PHP 8.4).

# 2. Phase 1 — Project initialization & tooling

Goal: an empty but runnable mono-repo with both apps booting, CI green, versions locked per the Tech Stack doc.

1. Initialize the mono-repo: root README, .gitignore, .editorconfig, /docs populated with the five source documents, .nvmrc = 24.

2. Backend scaffold (Tech Stack §3): composer create-project laravel/laravel backend "^12.0"; set PHP ^8.4. Commit composer.lock.

3. Install backend dependencies exactly per Tech Stack §3: laravel/sanctum ^4.3, spatie/laravel-permission ^7.4, spatie/laravel-activitylog ^5.0, spatie/laravel-backup, barryvdh/laravel-dompdf ^3.1; dev: pestphp/pest ^4, pest-plugin-laravel, laravel/pint, larastan/larastan.

4. Frontend scaffold (Tech Stack §4): npm create vite@latest frontend -- --template react-ts; install react-router-dom ^7.18, @tanstack/react-query ^5.101, react-hook-form ^7.55, @hookform/resolvers ^5, zod ^4.4, axios ^1.9, @headlessui/react ^2.2, tailwindcss ^4.3 + @tailwindcss/vite ^4.3, plus the Design System §4 additions: lucide-react, clsx, tailwind-merge, recharts ^3, @tanstack/react-table ^8, react-day-picker ^9, sonner ^2, @radix-ui/react-tooltip. Dev: vitest ^4, @testing-library/react ^16, @testing-library/jest-dom ^6, @testing-library/user-event ^14, jsdom, eslint, prettier. Commit package-lock.json.

5. Configure tooling: Pint + Larastan (backend); ESLint + Prettier + TypeScript strict (frontend); Husky/lint-staged optional.

6. CI pipeline: lint + Pint + Larastan + Pest (backend); typecheck + ESLint + Vitest + vite build (frontend); spin a PostgreSQL 17 service for backend tests.

7. .env.example for both apps (no secrets) capturing every key from Tech Stack §5 and Schema §1.1.

⛔ DoD: php artisan serve boots; npm run dev boots; npm run build succeeds; CI is green on an empty test; both lockfiles committed.

# 3. Phase 2 — Backend foundation & database connections

Goal: Laravel wired to PostgreSQL 17 with the two-role RLS connection model and the per-request session-context middleware.

1. Provision PostgreSQL 17 locally; create database; CREATE EXTENSION citext; (Schema §10).

2. Create the two DB roles (Schema §1.1): hairbeauty_owner (BYPASSRLS, owns objects, runs migrations/seeders/jobs) and hairbeauty_app (NOBYPASSRLS, used by web requests); apply the grants and default privileges.

3. Define two Laravel connections in config/database.php: pgsql (role hairbeauty_app) and pgsql_owner (role hairbeauty_owner). Migrations run with --database=pgsql_owner.

4. Implement SetDbSessionContext middleware (Schema §2.3): after auth, SET app.user_id / app.role / app.location_ids on the pgsql connection; RESET in finally. Register on the authenticated API group.

5. Configure .env drivers (Tech Stack §5): CACHE_STORE=database, SESSION_DRIVER=database, QUEUE_CONNECTION=database, FILESYSTEM_DISK=local, MAIL_MAILER=smtp. Run the framework migrations for jobs/cache/sessions on the owner connection.

6. Establish the JSON error envelope and base API response conventions (Schema §9): { message, errors, code }; register exception handler mappings (validation → 422, auth → 401, locked password → 423, RLS/forbidden → 403).

⛔ DoD: app connects as hairbeauty_app; a smoke test sets the GUCs and reads them back via current_setting; framework tables exist; error envelope returns for a forced 422.

# 4. Phase 3 — Database schema (the canonical build order)

Goal: the entire schema, functions, triggers, views, and RLS policies, created in the exact order of Schema §10, as pgsql_owner migrations.

1. Enum types (Schema §3) — one migration creating all CREATE TYPE enums.

2. Identity, RBAC, assignment (Schema §4.1): users, spatie tables, personal_access_tokens, user_locations. Seed the permission catalogue + roles (admin/seller/store_keeper) here or in Phase 4 seeders.

3. Locations & settings (Schema §4.2): locations (+ single-central-store partial unique index), settings, location_settings.

4. Catalogue & batches (Schema §4.3): categories, suppliers, products, product_batches.

5. Inventory & ledger (Schema §4.4): stock_movements, inventory.

6. Purchasing (Schema §4.5): purchases, purchase_items, then the deferred product_batches.purchase_item_id FK.

7. Distribution (Schema §4.6): distributions, distribution_items, discrepancies.

8. Sales & reconciliation (Schema §4.7–4.8): clients (needed by sales), sales, sale_items, daily_reconciliations.

9. Operations (Schema §4.9–4.10): attendances, expense_categories, expenses, alerts, announcements, announcement_reads, report_runs.

10. Functions, triggers, views (Schema §7): set_updated_at + triggers; fn_apply_stock_movement + trigger; fn_refresh_latest_cost; fn_sale_item_snapshot; fn_confirm_distribution; fn_revert_sale; v_expected_sales_by_day; fn_profit_summary; the four SECURITY DEFINER alert generators.

11. RLS (Schema §5): session helper functions; ENABLE/FORCE ROW LEVEL SECURITY on every business table; the P1–P4 policies for each table per the §5.2 summary.

12. Indexes (Schema §6): confirm every listed index exists (most are inline in the DDL).

⛔ DoD (migration-order gate): a fresh migrate:fresh --database=pgsql_owner succeeds end-to-end; all enums/tables/functions/triggers/policies present; a trigger test proves stock_movements insert updates inventory and blocks negative stock (Schema §7.2).

# 5. Phase 4 — Authentication & RBAC

Goal: Sanctum auth, forced password change, and the full permission model enforced at all three layers.

1. Seeders (Schema §10 step 12): permissions + roles; the first admin (must_change_password=true); central store + three shops; six system expense categories; settings defaults.

2. Configure Sanctum token auth (Tech Stack §4, Schema §2.1); model User with spatie HasRoles; relations to locations via user_locations.

3. Auth endpoints (Schema §9.1): POST /auth/login, POST /auth/logout, GET /auth/me, POST /auth/change-password. Login returns user, role, permissions, locations, must_change_password.

4. Password-change gate middleware: any authenticated request other than change-password/logout returns 423 with password_change_required while the flag is set.

5. Wire SetDbSessionContext (Phase 2) into the authenticated flow so RLS context is populated from the resolved user's role + assigned locations.

6. Write Policies for User and a base policy pattern other modules will follow; register permission middleware aliases.

⛔ DoD (RLS isolation gate — foundational): automated tests prove that, as hairbeauty_app with a seller context, selecting another shop's rows returns zero and inserting for another shop is rejected — asserted on at least users and one P2 table now, and re-run per module hereafter (Schema §10 verification gate).

# 6. Phase 5 — Core domain backend modules (dependency-ordered)

Build each module as a vertical slice (migration already exists from Phase 3 → model → policy → service → controller → routes → Pest tests → RLS gate). Order respects data dependencies.

1. Locations & Settings admin — CRUD for shops/store, geofence radius, thresholds (expiry 60d, low-stock 30d cover, restock 3mo, shift 1mo, wholesale_min_qty 12, geofence 100m). Governs: PRD settings, Schema §4.2.

2. Users & roles management — admin creates sellers/store-keepers, assigns role + location, activate/deactivate, reset to forced-change. Schema §4.1, §9.5.

3. Catalogue — categories, suppliers, products (retail/wholesale price, wholesale_min_qty, reorder level). Schema §4.3.

4. Inventory & ledger services — read APIs for balances and movements; the ledger is written only by purchase/distribution/sale/revert services via stock_movements (trigger maintains inventory). Schema §4.4, §7.2.

5. Purchasing — record purchase → create batch per line → purchase_in movement → fn_refresh_latest_cost. Schema §4.5, §7.3.

6. Distribution — store-keeper sends (writes distribution_out, status pending); seller confirms via fn_confirm_distribution (received → shop; shortfall auto-returns to store; discrepancy logged). Schema §4.6, §7.4.

7. Sales (POS) — FIFO batch allocation by expiry; per-line tier (qty ≥ wholesale_min_qty → wholesale) and price; cost snapshot per consumed batch; sale_out movements; payment method recorded (no cash). Admin revert via fn_revert_sale. Schema §4.7, §7.3, §7.5.

8. Daily reconciliation — seller submits declared bank total + uploads receipt; expected_total from v_expected_sales_by_day; variance + status; monitoring only. Schema §4.8, §7.6.

9. Attendance — punch-in/out sessions; server validates geofence against locations (Haversine, radius default 100m); store lat/lng, within_geofence, source (online/offline). Schema §4.9, PRD attendance.

10. Expenses & Clients — expenses (category, optional location, amount, date, note); clients per shop (brand, phone non-unique, area), optional on sale. Schema §4.10.

11. Alerts & recommendations — read/dismiss APIs; generation handled in Phase 7. Schema §4.10.

12. Announcements — admin CRUD; visible to all; read tracking. Schema §4.10.

13. Reports — report_runs records; generation in Phase 7. Schema §4.10.

14. Dashboard & profit — KPIs + fn_profit_summary(location, from, to) (gross − expenses), per-shop and overall, date-range filtered. Schema §7.6, PRD profit.

⛔ DoD: each module's feature tests pass; the RLS isolation gate re-runs green for every P2/P3 table; ledger invariants hold (no negative stock; profit = Σ line_profit − expenses on a seeded scenario).

# 7. Phase 6 — API layer hardening

Goal: a consistent, validated, documented REST surface under /api/v1 (Schema §9).

1. Normalize all routes to /api/v1, resource-style; attach permission middleware + policies to each (Schema §9.1–9.5).

2. Form Requests mirror DB constraints (Schema §4) for every write endpoint; consistent validation error envelope.

3. API Resources for response shaping; raw ISO-8601 UTC datetimes and numeric money (frontend formats per Design System §5).

4. Page-based pagination, filtering, and sorting conventions applied uniformly.

5. Rate-limit auth endpoints; enforce Sanctum abilities; CORS + Sanctum stateful domains configured for the SPA origin.

6. Generate API reference (OpenAPI or a documented Postman/Bruno collection) from the route list.

DoD: every endpoint has a feature test (happy + auth-failure + validation-failure); API reference generated; no route lacks all three authz layers.

# 8. Phase 7 — Scheduled jobs, alerts, reports & backups

Goal: all background automation on the single-cron + database-queue model (Tech Stack §5).

1. Wire the Laravel scheduler (one cron entry) and a scheduled queue:work for the database queue (no Supervisor).

2. Alert/recommendation generation (Schema §7.7): schedule fn_generate_expiry_alerts, fn_generate_low_stock_alerts, fn_generate_restock_recommendations, fn_generate_shift_recommendations (run as owner / SECURITY DEFINER); idempotent via the active-alert dedupe index.

3. Automated reports (PRD): weekly + monthly PDF (dompdf) of sales/profit/inventory; email via SMTP to admins with reports.receive; persist to report_runs.

4. Backups (Tech Stack §5, PRD): spatie/laravel-backup — database backup daily, full application backup weekly, to the configured disk.

5. In-app notifications: surface generated alerts to the alerts bell; weekly/monthly report-ready notices.

DoD: scheduler dry-run lists all jobs; generating alerts twice produces no duplicates; a weekly report PDF renders and emails in a test; a backup run completes.

# 9. Phase 8 — Frontend foundation

Goal: the design system materialized and the authenticated app shell, before any feature page.

1. Tailwind v4 @theme block into src/styles/app.css exactly per Design System §3; configure the @tailwindcss/vite plugin; load Inter + JetBrains Mono.

2. Utilities: src/lib/cn.ts (§6.0) and src/lib/format.ts (§5 — formatCurrency "TZS 12,500", formatDate DD/MM/YYYY, EAT, etc.). Never hand-format elsewhere.

3. API client & auth: axios instance with bearer-token interceptor + 401/423 handling; TanStack Query setup; auth store; protected-route wrapper; React Router v7 routes.

4. Component library src/components/ui/* per Design System §6, each with all states and a11y: Button, Input/Textarea, Select, Checkbox/Radio/Toggle, Card/KPI, Modal, StatusPill, Alert, Dropdown, Toast (sonner Toaster), Table (TanStack), Pagination, Tabs, Breadcrumbs, Avatar, Empty/Loading/Error, Tooltip, DatePicker. Unit-test each.

5. App shell (Design System §7): sidebar nav (navy, permission-filtered), top bar (logo wordmark "BeautyIntel", global search, shop-context select, punch widget, alerts bell, user menu), responsive drawer below lg.

6. Auth screens: login + forced password-change, wired to Phase 4 endpoints.

⛔ DoD: Storybook-style or a component gallery renders every ui/* component; login works end-to-end against the backend; a11y checks pass on the shell and components; vite build clean.

# 10. Phase 9 — Frontend feature modules (mapped to App Flow)

Build per the App Flow document, each feature gated by its backend module (Phase 5) and reusing only ui/* components and tokens (Design System §11). Sequence:

1. Dashboard — KPI cards, profit (date range), trend charts (Recharts per Design System §8), recent activity/alerts.

2. Products & catalogue — list/detail/form (list/detail/form templates, Design System §7.4).

3. Inventory — balances by location, movement history, low-stock/expiry surfacing.

4. Purchasing — record purchase (batch, cost, expiry).

5. Distribution — store: send to shop; shop: confirm receipt with per-line received qty, discrepancy display (auto-return messaging).

6. Sales (POS) — line-item entry, auto tier pill, FIFO transparent, payment method, client (optional); admin revert with reason.

7. Reconciliation — daily submit: declared total + receipt upload; expected vs declared variance view.

8. Attendance — punch in/out with browser geolocation + geofence check; offline queue when within geofence; live session timer; monitoring views for admin.

9. Expenses & Clients — CRUD lists/forms.

10. Alerts center & Announcements/news — alert list (read/dismiss), announcements feed.

11. Reports — list + download generated PDFs.

12. Users & roles, Settings — admin management screens (RBAC, thresholds, geofence, shops).

DoD: each feature matches its App Flow screens and Design System states (empty/loading/error), passes Vitest component tests, and respects permissions (UI hides what the role can't do; backend still enforces).

# 11. Phase 10 — Cross-cutting polish

1. Accessibility (WCAG 2.1 AA) sweep across all pages (Design System §10): focus rings, keyboard nav, ARIA, contrast, status-by-icon+label, reduced-motion.

2. Responsive behavior: stacked-card table reflow below md, mobile POS/forms, sidebar drawer (Design System §7.5).

3. Microcopy pass per Design System §9 (fixed geofence/offline strings, verb buttons, recoverable errors).

4. Performance: query keys/caching, list pagination, image/asset budget, code-splitting per route.

5. Observability: structured logging, spatie/activitylog audit coverage on create/update/revert/confirm; error boundary + toast on API failures.

DoD: Lighthouse/a11y audits pass AA; no layout breaks across breakpoints; audit log captures the sensitive actions.

# 12. Phase 11 — Testing & QA hardening

1. Backend (Pest): feature tests per endpoint; unit tests for services (FIFO, tier, cost snapshot, profit, confirm-distribution auto-return, revert); the RLS isolation suite across every P2/P3 table (Schema §10 gate).

2. Frontend (Vitest + Testing Library): component states, form validation (zod), guarded routes, formatters.

3. End-to-end happy paths: login → forced password change; record purchase → distribute → confirm (with shortfall) → sell → revert; submit reconciliation; punch in/out.

4. Seeded demo dataset for manual UAT mirroring the real shop setup.

5. Fix-and-stabilize; ensure CI runs the full matrix.

⛔ DoD: full test matrix green in CI; RLS isolation gate green for all tables; critical E2E flows pass.

# 13. Phase 12 — Data migration (legacy MySQL → PostgreSQL)

1. Map legacy MySQL entities to the new schema (products, stock, clients, historical sales/expenses as applicable). Document field-by-field mapping.

2. Build a one-off ETL (Artisan command run as pgsql_owner): extract → transform (units, money to numeric, timezones to UTC) → load; create opening batches and opening-balance stock_movements so inventory is correct via the trigger.

3. Reconcile: counts and money totals legacy vs migrated; spot-check; sign-off checklist.

4. Dry-run against a staging copy; capture rollback procedure.

⛔ DoD: migrated counts and balances reconcile to source within agreed tolerance; opening inventory matches physical/last-known stock; run is repeatable and reversible.

# 14. Phase 13 — Deployment to DirectAdmin (VPS)

Per Tech Stack §5 and Schema §1.1. Assets built locally/CI, deployed compiled.

1. Provision: confirm PHP 8.4 in the DirectAdmin PHP selector with required extensions (Tech Stack §2: pdo_pgsql, mbstring, gd, zip, …); PostgreSQL 17 database + the two roles; CREATE EXTENSION citext.

2. Secrets/env: production .env (DB on pgsql/pgsql_owner, SMTP via DirectAdmin, app key, Sanctum stateful domains/CORS for the SPA host).

3. Database: run migrations as pgsql_owner (migrate --force --database=pgsql_owner); run seeders; execute the Phase 12 ETL; verify RLS is forced.

4. Backend deploy: ship code via SSH/Git; composer install --no-dev --optimize-autoloader; config:cache route:cache view:cache; storage symlink; queue/cache tables present.

5. Frontend deploy: npm ci && npm run build locally/CI; deploy dist/ as static assets (docroot or app. subdomain); API under /api (or api. subdomain); confirm CORS/Sanctum.

6. Scheduler & queue: add the single cron entry (* * * * * php artisan schedule:run); confirm scheduled queue:work and alert/report/backup jobs.

7. Backups: verify spatie/laravel-backup daily DB + weekly app backups land on the configured disk; test a restore.

8. Smoke test production: login, a sale, a distribution-confirm, reconciliation submit, an alert generation, a report email.

⛔ DoD: production smoke tests pass; RLS enforced in prod; backups + scheduler verified; HTTPS, CORS, and mail working.

# 15. Phase 14 — Launch & post-launch

1. Go-live (target 01/08/2026): final data refresh/ETL cutover; create real user accounts (forced password change); brief admins.

2. Hypercare: monitor logs, queue, failed jobs, and backups daily for the first two weeks; triage issues fast.

3. Post-launch backlog: defer-list items (e.g., dark mode, Laravel 13 upgrade, PG 18, split-payment, per-role announcements) tracked for v1.1 per the source docs' "not now" notes.

4. Handover: runbook (deploy, restore, rotate secrets, add a shop/user), and the five source documents as the living spec.

DoD: real users transacting; backups/restores verified in prod; hypercare checklist clear.

# 16. Sequencing summary (milestones)

| Milestone | Phases | Exit gate |
| --- | --- | --- |
| M1 — Skeleton | 1–2 | Both apps boot; CI green; DB roles + RLS middleware live |
| M2 — Schema | 3–4 | Migration-order gate + foundational RLS isolation gate pass |
| M3 — Backend domain | 5–7 | All modules + APIs + scheduled jobs tested; RLS gate per table |
| M4 — Frontend | 8–10 | Design system + shell + all feature screens; a11y AA |
| M5 — Hardening | 11 | Full test matrix + E2E green |
| M6 — Data & deploy | 12–13 | ETL reconciled; production smoke tests pass |
| M7 — Launch | 14 | Real users live; backups/scheduler verified |

# 17. Master verification gates (must all pass before launch)

1. Migration-order gate — migrate:fresh builds the entire Schema §10 order cleanly.

2. Inventory-invariant gate — ledger trigger maintains balances; negative stock blocked.

3. RLS isolation gate — cross-shop read/write denied for non-admins on every P2/P3 table.

4. Profit-correctness gate — fn_profit_summary = Σ line_profit − expenses on seeded data; cost snapshots stable after later cost changes.

5. Distribution auto-return gate — shortfall returns to central store + discrepancy logged.

6. Auth gate — forced password change enforced; tokens revoked on logout; three-layer authz on every endpoint.

7. Backup & scheduler gate — daily DB + weekly app backups; single-cron jobs (alerts/reports) run and are idempotent.

8. Accessibility gate — WCAG 2.1 AA across the app.